## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File
1241282 | 12735 | Movie Rental Application | 1 | MOVIERENTALAPPLICATION-1 | 53204 | Bug |  |  | 7490 | 1.0 | Importing data files | Test case 9: Load Customer info and choose not to delete current records Expected results: File loads without errors, both old and current customer db are populated Actual results: File does load on first attempt. If user selects not to delete again program crashes. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51664 | Tracy Zeigler | Dec. 02, 2018 14:47 | Dec. 31, 2018 | 51664 | Tracy Zeigler | Dec. 02, 2018 14:47 | 0 | 0
1241283 | 12735 | Movie Rental Application | 2 | MOVIERENTALAPPLICATION-2 | 53204 | Bug |  |  | 7490 | 1.0 | Application Crash - Uploading wrong data | Test Case 10 Test Condition: Load wrong file to a database Expected Results: Message appears with choice to go back to last step Actual results: when uploading Movie Data file instead of client.txt program crashes | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51664 | Tracy Zeigler | Dec. 02, 2018 14:49 | Dec. 31, 2018 | 51664 | Tracy Zeigler | Dec. 02, 2018 14:49 | 0 | 0
1241285 | 12735 | Movie Rental Application | 3 | MOVIERENTALAPPLICATION-3 | 53204 | Bug |  |  |  |  | Name search is not working | Test Condition: Lack of one or more of these fields: ID, first name, last name, address, city, state, and zipcode Expected Results: Message appears that these fields are required and customer was not added Actual results: After incorrect entry (firstname in place of userid and lastname blank) error is given but program does not crash. (i.e first incorrect entry was accepted but correct reentry has issue) | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51664 | Tracy Zeigler | Dec. 02, 2018 15:04 | Dec. 31, 2018 | 51664 | Tracy Zeigler | Dec. 02, 2018 15:04 | 0 | 0
1241313 | 12735 | Movie Rental Application | 4 | MOVIERENTALAPPLICATION-4 | 53204 | Bug |  |  | 7490 | 1.0 | Load Screen | When load customer info and choose not to delete current records from db, program crashes. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:08 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:17 | 0 | 0
1241314 | 12735 | Movie Rental Application | 5 | MOVIERENTALAPPLICATION-5 | 53204 | Bug |  |  | 7490 | 1.0 | Load screen 2 | When load wrong file in database, the program crashes. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:12 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:19 | 0 | 0
1241315 | 12735 | Movie Rental Application | 6 | MOVIERENTALAPPLICATION-6 | 53204 | Bug |  |  | 7490 | 1.0 | Customer menu | first incorrect entry was accepted but correct reentry has issue. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:14 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:18 | 0 | 0
1241316 | 12735 | Movie Rental Application | 7 | MOVIERENTALAPPLICATION-7 | 53204 | Bug |  |  | 7490 | 1.0 | customer menu 2 | When search an unexisting name, search doesn't return and no message is displayed. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:16 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:16 | 0 | 0
1241317 | 12735 | Movie Rental Application | 8 | MOVIERENTALAPPLICATION-8 | 53204 | Bug |  |  | 7490 | 1.0 | Rental Menu | missing customer ID or date rented info, neither affect response message. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:21 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:21 | 0 | 0
1241318 | 12735 | Movie Rental Application | 9 | MOVIERENTALAPPLICATION-9 | 53204 | Bug |  |  | 7490 | 1.0 | Rental Menu 2 | missing movie ID brings multiple issues. | 1 | Open | 3 | Normal |  |  |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:22 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:22 | 0 | 0
1241319 | 12735 | Movie Rental Application | 10 | MOVIERENTALAPPLICATION-10 | 53204 | Bug |  |  | 7490 | 1.0 | Rental Menu 3 | a. Movie ID and title does not match when returning it b. CUSTOMER ID and rented MOVIE ID does not match when returning the movie c. DATE RETURNED is before DATE RENTED under these situations the movie is returned anyway. | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:25 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:25 | 0 | 0
1241320 | 12735 | Movie Rental Application | 11 | MOVIERENTALAPPLICATION-11 | 53204 | Bug |  |  | 7490 | 1.0 | Employee Menu | when Passwords do not match, Employee added anyway | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:26 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:26 | 0 | 0
1241321 | 12735 | Movie Rental Application | 12 | MOVIERENTALAPPLICATION-12 | 53204 | Bug |  |  | 7490 | 1.0 | Employee Menu 2 | Duplicate employee (the same first name and last name), Employee will be readded | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:26 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:26 | 0 | 0
1241322 | 12735 | Movie Rental Application | 13 | MOVIERENTALAPPLICATION-13 | 53204 | Bug |  |  | 7490 | 1.0 | Employee Menu 3 | Delete when Employee DB is empty, the Delete message still appears | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:27 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:27 | 0 | 0
1241323 | 12735 | Movie Rental Application | 14 | MOVIERENTALAPPLICATION-14 | 53204 | Bug |  |  | 7490 | 1.0 | Employee menu 4 | When Change password error message still given when correct entry | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:28 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:28 | 0 | 0
1241325 | 12735 | Movie Rental Application | 15 | MOVIERENTALAPPLICATION-15 | 53204 | Bug |  |  | 7490 | 1.0 | Employee Menu - name | FIRST NAME or LAST NAME do not match with the record, message still given | 1 | Open | 3 | Normal | 7490 | 1.0 |  |  | 51664 | Tracy Zeigler | 51666 | Lucy | Dec. 02, 2018 18:30 | Dec. 31, 2018 | 51666 | Lucy | Dec. 02, 2018 18:30 | 0 | 0